## Project Details
PSP for WIFI HANGMAN PROJECT
STUDENT NAME(S) : | ASMA MEHJABEEN
KEERTHANA ARAVAMUDHAN
INSTRUCTOR : | DR WIllIAM HONIG
COURSE : | SOFTWARE DEVELOPMENT FOR MOBILE APPLICATIONS
PROJECT NAME: | WIFI HANGMAN PROJECT
FALL 2013
LANGUAGE: | ANDROID

## Summary
SOFTWARE METRICS FOR WIFI HANGMAN PROJECT
Summary | Planned | Actual | Date
Lines of Code(LOC)+Comments | 1400 | 2300 | 2013-12-01
Time for Each Phase | Planned | Actual | Date
Requirement Analysis | 10 | 12 | 2013-11-09
Planning and Design | 20 | 14 | 2013-11-12
Incremental Development | 30 | 42 | 2013-11-28
Test | 10 | 16 | 2013-11-30
Implementation | 4 | 6 | 2013-12-01
TOTAL | 74 | 90
| Defects Injected | Actual
| Requirement Analysis | 1
| Planning and Design | 3
| Incremental Development | 10
| Test | 4
| Implementation | 2
| TOTAL | 20
| Defects Removed | Actual
| Requirement Analysis | 0
| Planning and Design | 3
| Incremental Development | 10
| Test | 4
| Implementation | 2
| TOTAL | 19

## Hangman Module
SOFTWARE METRICS FOR HANGMAN MODULE
Summary | Planned | Actual | Date
Lines of Code(LOC)+Comments | 900 | 1500 | 2013-12-01
Time for Each Phase | Planned | Actual | Date
Requirement Analysis | 5 | 7 | 2013-11-01
Planning and Design | 10 | 13 | 2013-11-08
Incremental Development | 10 | 22 | 2013-11-28
Test | 5 | 5 | 2013-11-30
Implementation | 2 | 2 | 2013-12-01
TOTAL | 32 | 49
| Defects Injected | Actual
| Requirement Analysis | 0
| Planning and Design | 2
| Incremental Development | 8
| Test | 4
| Implementation | 2
| TOTAL | 16
| Defects Removed | Actual
| Requirement Analysis | 0
| Planning and Design | 2
| Incremental Development | 8
| Test | 4
| Implementation | 2
| TOTAL | 16

## WIFI DIRECT MODULE
SOFTWARE METRICS FOR WIFI DIRECT MODULE
Summary | Planned | Actual | Date
Lines of Code(LOC)+Comments | 500 | 1150 | 2013-11-23
Time for Each Phase | Planned | Actual | Date
Requirement Analysis | 5 | 6 | 2013-11-09
Planning and Design | 10 | 7 | 2013-11-12
Incremental Development | 15 | 21 | 2013-11-23
Test | 5 | 8 | 2013-11-23
Implementation | 2 | 3 | 2013-11-23
TOTAL | 37 | 45
| Defects Injected | Actual | Description of defect
| Requirement Analysis | 1 | Could not send system level notification since it is not supported by Wifi direct
| Planning and Design | 1 | Used discover peers instead of discovering services
| Incremental Development | 2 | Sockets did not connect properly at times, Wi-fi connection problems
| Test | 0
| Implementation | 0
| TOTAL | 4
| Defects Removed | Actual
| Requirement Analysis | 0
| Planning and Design | 1
| Incremental Development | 2
| Test | 0
| Implementation | 0
| TOTAL | 3